## DFM template
NEXTPCB DFA report
Project Number： |  | Prepared by: |  |  |  |  | Date: 20250806
Item | Problem description 问题描述 | Reference location 影响位置 | MPN 物料名称 | Impact 影响 | Image 图片 | NextPCB Suggestion 建议 | Customer feedback 客户反馈 | Severity 严重度 | Status 状态
1 | The coordinate fie is lack of the coordinate information of SW1,SW2.Are their positions as shown in the picture? | SW1,SW2 |  |  |  | Pls confirm. | SW1 = BOOT, SW2 = EN | High | open
2 | The pitch of pads should be 2.54mm.The package in gerber is too small. | J1 |  | It will cause soldering issue.The component can not be soldered on the pads. |  | please modify the package according to the datasheet. | The component is wrong, it should be 1.27mm spacing. M50-3630542. Leave open I can also put it. | High | open
3 | The package is lack of two holes.The diameter of holes should be 1.2mm and the pitch of holes should be 2.54mm. | J5,J7 |  | It will cause soldering issue.The component can not be inserted into the holes. |  | please modify the package according to the datasheet. | Leave open, place the component in the box. I will see what I can do with it. | High | open
4 | The pitch of pads should be 6.8mm according to the datasheet. | J3 |  | It will cause soldering issue.The component can not be soldered on the pads. |  | please modify the package according to the datasheet. | 693072010801 this is the correct component for this footprint. I have order it twice with Next PCB already different version of this board. | High | open
5 | The pitch of pads should be 0.65mm. | Q1,Q2 |  | It will cause soldering issue.The component can not be soldered on the pads. |  | please modify the package according to the datasheet. | The components is correct and the footprint is correct. Previous version of the board manufactured by NextPCB was the same and the component and footprint did match. | High | open
6 | Which side is anode？ | C16,C15,C10,C22,C4,C2 |  |  |  | please point out in silk layer. | Adjsuted email new gerber files please see attachment. | High | open